## Slide 1: Lean Construction Contractor Survey 2021
Dana Gilmore Research Project Manager Industry Insights & Research Communications dana.gilmore@construction.com
August 2021

## Slide 2: Table of Contents
 | Page Number
Objectives | 3
Methodology | 4
Demographics | 5
Findings | 
Selection of projects | 16
Project outcomes | 21
Organizational factors | 35
Commercial factors | 41
Process/operational factors | 52

## Slide 3: Objectives
  The 2021 Lean Construction Study was conducted among contractors in the US. The objectives included:
    Benchmarking project performance metrics across two project types: “Typical” and “Best Performing”.
    Look at the use of Lean practices, such as organizational factors, commercial factors and process/operational practices on the best and typical projects.
  Specific Areas of Inquiry Include:
    Firm Profile
    Selection of Best v. Typical projects
    Project Outcomes
    Organizational Factors
    Commercial Factors
    Process/Operational Factors

## Slide 4
Methodology
Online survey questionnaire completed by 336 respondents:
  Respondents came from the DD&A contractor panel and from The Associated General Contractors of America
  The survey was open from June 15th, 2021, to June 18th, 2021, for Contractor Panel respondents and from June 1st , 2021 to July 2nd, 2021, for AGC respondents
  Average survey length was just over 18 minutes
Survey Criteria:
  Survey was open to contractor firms who work in the United States
General, specialty, and heavy civil contractors were included
  Firms with over 50% single-family residential or over 50% industrial projects were excluded from the survey
Technical notes:
    Unless other wise noted, the sample size for charts is 278
    187 respondents were classified as general contractors, 108 as specialty/trade contractors, and 41 as heavy civil contractors
    An “*” is used to denote where significant differences between groups exist, p < .05
    After the demographics sections, differences by company type are only noted where there is a statistically significant difference.

## Slide 5: Demographics
Unless otherwise noted sample size is:
Total: 336 respondents
GC/CM: 187
Specialty/trade: 108
Heavy civil: 41

## Slide 6: Demographics: Firm Type and Job Role
qa1. Which of the following best describes your company?
qa3b: What percentage of your firm’s projects are civil/horizontal projects?
A good representation of general, specialty, and heavy civil contractors were included
To be considered a heavy civil contractor more than 50% of that firm's projects were civil/horizontal
Chart: Firm type
| GC/CM, n=187 | Specialty, n=108 | Heavy Civil, n=41
Total | 0.55655 | 0.32143 | 0.12202
Chart: % civil/horizontal projects
| GC/CM, n=55 | Specialty, n=27 | Heavy Civil, n=41
Less than 25% | 0.61818 | 0.85185 | 0
25% to 49% | 0.38182 | 0.14815 | 0
50% to 74% | 0 | 0 | 0.2439
75% or more | 0 | 0 | 0.7561

## Slide 7: Demographics: Subcontractor Services
qa4b. What type of subcontracting services does your firm primarily offer for your projects?
A broad array of specialty contractor types were included
Mechanical, HVAC, plumbing and electrical were most common
Chart: Subcontracting services: Top 10
| Steel erection/fabrication | Concrete | Fire protection | Roofing | Thermal and moisture control | Carpentry/framing | Electrical | Plumbing | HVAC/sheet metal | Mechanical
Total | 0.074074 | 0.11111 | 0.11111 | 0.12037 | 0.13889 | 0.17593 | 0.2037 | 0.23148 | 0.24074 | 0.24074

## Slide 8: Demographics: Heavy Civil Specialty Services
qa4a. What type of subcontracting services does your firm primarily offer for your civil projects?
16 specialty firms were considered heavy civil, based on their project types
Many civil project services were included, primarily storm drainage, erosion/sediment control, and concrete
Chart: Civil project contracting services: Top 10
| Highway and overhead signs | Masonry | Piles/caissons | Bridge/retaining wall | Line striping | Demolition/wrecking | Paving | Concrete | Erosion and sediment control | Storm drainage/wet utility
Heavy Civil | 0.1875 | 0.1875 | 0.1875 | 0.25 | 0.25 | 0.3125 | 0.3125 | 0.375 | 0.375 | 0.625

## Slide 9: Demographics: Project Types
qa2. What types of projects are in your company's contracting portfolio?
Over 20 different project types were included, the top 11 are listed below
Specialty and GC firms worked mostly on building projects
Chart: Project types: Top 11
| Laboratories | Apartments and multi-family housing units | Manufacturing | Warehouse/distribution | Hospitality/hotel | Education (K-12) | Education (higher education) | Retail | Hospitals/other healthcare buildings | Public buildings (e.g., government) | Office
GC/CM | 0.37433 | 0.45989 | 0.41176 | 0.51337 | 0.48663 | 0.5508 | 0.55615 | 0.63102 | 0.63102 | 0.65241 | 0.80749
Specialty | 0.5463 | 0.47222 | 0.58333 | 0.60185 | 0.68519 | 0.68519 | 0.74074 | 0.75 | 0.77778 | 0.76852 | 0.85185
Heavy Civil | 0.12195 | 0.17073 | 0.17073 | 0.21951 | 0.17073 | 0.19512 | 0.21951 | 0.21951 | 0.2439 | 0.26829 | 0.19512

## Slide 10: Demographics: Project Types
qa2. What types of projects are in your company's contracting portfolio?
The heavy civil firms worked mostly on civil or horizontal projects
These projects were less frequently cited as there were fewer heavy civil contractors than GC or specialty firms
Chart: Project types: Bottom 11
| Other | Heavy rail | Transit | Single-family housing | Federal non-building projects | Utilities (including generation and transmission) | Industrial projects (e.g., oil and gas plants) | Heavy civil/highway | Water | Data centers | Entertainment (e.g., stadiums, theme parks)
GC/CM | 0.02139 | 0.02139 | 0.069519 | 0.1016 | 0.13369 | 0.14439 | 0.14439 | 0.11765 | 0.13369 | 0.26738 | 0.3262
Specialty | 0.046296 | 0.018519 | 0.083333 | 0.17593 | 0.092593 | 0.11111 | 0.21296 | 0.055556 | 0.18519 | 0.5 | 0.50926
Heavy Civil | 0.073171 | 0.097561 | 0.19512 | 0.02439 | 0.26829 | 0.43902 | 0.19512 | 0.82927 | 0.4878 | 0.097561 | 0.12195

## Slide 11: Demographics: Project Classification
qa5: With which types of projects have you personally had most experience in the last five years?
GC and specialty firms worked mostly on new construction
Most heavy civil projects were rehabilitation
Chart: Project classification
| Expansion | Replacement | New construction (greenfield) | Tenant improvement | Rehabilitation | Renovation | New construction/major addition
GC/CM | 0 | 0 | 0 | 0.064171 | 0 | 0.18182 | 0.75401
Specialty | 0 | 0 | 0 | 0.046296 | 0 | 0.21296 | 0.74074
Heavy Civil | 0.14634 | 0.17073 | 0.26829 | 0 | 0.41463 | 0 | 0

## Slide 12: Demographics: Firm Size and Project Location
qa4: What was the value of your company’s revenue in 2020?
qa6. Please select the regions in which your completed construction projects in the past 3 years are located.
Firms of all sizes were included in the study
Firms conducted projects across the US
Chart: Firm size
| GC/CM | Specialty | Heavy Civil
< $50M | 0.37433 | 0.72222 | 0.5122
$50M to $500 million | 0.39572 | 0.22222 | 0.43902
$500M+ | 0.21925 | 0.018519 | 0.04878
Don’t know | 0.010695 | 0.037037 | 0
Chart: Project location
| New England | Middle Atlantic | East North Central | West North Central | South Atlantic | East South Central | West South Central (AR, LA, OK, TX) | Mountain | Pacific | Outside the US
GC/CM | 0.12834 | 0.19251 | 0.27273 | 0.18717 | 0.31016 | 0.15508 | 0.23529 | 0.22995 | 0.23529 | 0.048128
Specialty | 0.11111 | 0.10185 | 0.26852 | 0.14815 | 0.27778 | 0.12037 | 0.12963 | 0.14815 | 0.21296 | 0.027778
Heavy Civil | 0.04878 | 0.17073 | 0.31707 | 0.12195 | 0.21951 | 0.12195 | 0.073171 | 0.14634 | 0.14634 | 0.04878

## Slide 13: Demographics: BIM Use
qg1: On what percentage of your organization's projects valued over $10 million is BIM being used?
Most specialty and GC firms reported some level of BIM use
Heavy civil contractors were less likely to be BIM users
Chart: Frequency of BIM use
| *None | Less than 15% | 15-30% | 31-60% | More than 60% | *Don’t know
GC/CM | 0.28342 | 0.14439 | 0.1016 | 0.085561 | 0.3369 | 0.048128
Specialty | 0.28704 | 0.18519 | 0.037037 | 0.074074 | 0.25926 | 0.15741
Heavy Civil | 0.60976 | 0.17073 | 0.073171 | 0.02439 | 0 | 0.12195

## Slide 14: Demographics: Lean Construction Familiarity
qg2: Are you familiar with Lean in design and construction?
Most firms were familiar with Lean in design and construction
Heavy civil firms were less familiar with Lean than GC firms
Chart: Familiar with Lean
| *Yes | *No
GC/CM | 0.74866 | 0.25134
Specialty | 0.65741 | 0.34259
Heavy Civil | 0.53659 | 0.46341

## Slide 15: Demographics: Frequency of Lean Construction Use
qg3: To what degree does your company use Lean on your projects that are valued at over $10 million in construction cost?
70% of GC and specialty firms report some level of Lean construction use on projects valued over $10M
        Mostly if requested by owner
Most heavy civil contractors reported not using Lean construction at all on projects valued over $10M
Chart: Frequency of Lean use
| *Not at all | Only if owner requires it | Infrequently (Less than 10% of projects) | Sometimes (11% to 30% or projects) | Frequently (31% to 60% of projects) | *Very frequently (61% to 90% of projects) | *Always (More than 90% of projects) | Don’t know
GC/CM | 0.27807 | 0.16578 | 0.090909 | 0.096257 | 0.12299 | 0.1016 | 0.085561 | 0.058824
Specialty | 0.32407 | 0.28704 | 0.064815 | 0.055556 | 0.046296 | 0.018519 | 0.018519 | 0.18519
Heavy Civil | 0.56098 | 0.097561 | 0.12195 | 0.04878 | 0.02439 | 0.02439 | 0 | 0.12195

## Slide 16: Findings
Selection of Best v. Typical projects
Project Outcomes
Organizational Factors
Commercial Factors
Process/Operational Factors
Unless otherwise noted sample size is:
Total: 336 respondents
GC/CM: 187
Specialty: 108
Heavy civil: 41

## Slide 17: Best Project Selection
qb1. Among the categories below, select the two that were most influential in your choice of a best project:
Respondent firms typically relied on quality and profitability as determinants of “best” projects
Chart: Best project selection criteria
| GC/CM | Specialty | Heavy Civil
Quality | 0.71123 | 0.69444 | 0.68293
Safety | 0.18182 | 0.16667 | 0.29268
Profitability | 0.53476 | 0.80556 | 0.73171
Internal Team Culture | 0.31551 | 0.12037 | 0.19512
External Team Culture | 0.25668 | 0.21296 | 0.097561

## Slide 18: Best and Typical Project Classification
qb2. How would you classify the best and typical projects you select?
Best projects were most likely wholly private
Chart: Project classification
| Wholly Public | Wholly Private | Hybrid of Public and Private
Best | 0.22619 | 0.55357 | 0.22024
Typical | 0.29167 | 0.45833 | 0.25

## Slide 19: Best and Typical Project Classification
qb2. How would you classify the best and typical projects you select?
Civil contractors had a much higher share of wholly public projects than do the other types of contractors
Trades report a much higher share of hybrid projects among their typical projects and a higher share of wholly private projects their best projects.
GC/CMs report a higher share of wholly public projects in their best projects than their typical with the difference largely split between wholly private and hybrid projects for the share of typical projects that are higher than their best ones..
Best Projects | GC/CM | Trades | Civil
Wholly Public | 20% | 15% | 56%**
Wholly Private | 59% | 59% | 29%**
Hybrid of Public and Private | 21% | 26% | 15%
Typical Projects | GC/CM | Trades | Civil
Wholly Public | 29%** | 15%** | 66%**
Wholly Private | 55% | 45% | 7%**
Hybrid of Public and Private | 16%* | 40%* | 27%
* denote statistical difference with one factor
** denotes statistical difference with more than one factor

## Slide 20: Percentage of Work Self-Performed
qb1. Among the categories below, select the two that were most influential in your choice of a best project:
The amount of work self-performed did not vary between best and typical projects
Chart: Percentage of work self-performed
| None | Less than 10% | 11% to 24% | 25% to 49% | 50% to 74% | 75% or more
Best | 0.09434 | 0.28302 | 0.27358 | 0.12264 | 0.14151 | 0.084906
Typical | 0.09434 | 0.32075 | 0.23113 | 0.13679 | 0.13679 | 0.080189

## Slide 21: Findings
Selection of Best v. Typical projects
Project Outcomes
Organizational Factors
Commercial Factors
Process/Operational Factors
Unless otherwise noted sample size is:
Total: 336 respondents
GC/CM: 187
Specialty: 108
Heavy civil: 41

## Slide 22: Project Outcomes: Budget Variance
qc1. Considering the specific projects that you selected as your best and typical projects, how would you best describe the variance between the final cost of construction and the original budget expected at the time that you became involved?
Best projects were more likely to have a final cost lower than the original budget
Typical projects were more likely to have no variance from original budget
Chart: Budget variance
| *Final construction cost was lower than original budget | *No variance – final construction cost matched original budget | Final construction cost was higher than original budget by less than 6%
Best | 0.5119 | 0.27083 | 0.21726
Typical | 0.22619 | 0.44048 | 0.33333

## Slide 23: Project Outcomes: Budget Variance
qc1a. How much lower were the final projects costs from the original budget?
For projects with lower costs, there was no significant difference between best and typical projects on how much lower costs were
Chart: How much lower were costs
| Less than 3% | 3% to less than 6% | 7% to less than 10% | 10% or more
Best, n=172 | 0.24419 | 0.33721 | 0.15116 | 0.26744
Typical, n=76 | 0.28947 | 0.44737 | 0.17105 | 0.092105

## Slide 24: Project Outcomes: Budget Variance
qc1b. How much higher were the final projects costs from the original budget?
For projects with higher costs, there was no significant difference between best and typical projects on how much higher costs were
N.B., projects were restricted as to how much over budget they were to be included in the study, a 6% cap
Chart: How much higher were costs
| Less than 3% | 3% to less than 6%
Best, n=73 | 0.38356 | 0.61644
Typical, n=112 | 0.33036 | 0.66964

## Slide 25: Project Outcomes: Schedule Variance
qc2. Considering these same best and typical projects, how did the final schedule compare to the original schedule expected at the time that you became involved in the project?
Schedule variance differed across the board for best and typical projects
Best projects were more likely to be under schedule, typical projects were more likely to be either on schedule or over schedule
Chart: Schedule variance
| *Final schedule was shorter than original budget schedule | *No variance – final construction schedule matched the original | *Final construction schedule was longer than the original schedule by less than 10% of the original scope
Best | 0.33929 | 0.4494 | 0.21131
Typical | 0.03869 | 0.59226 | 0.36905

## Slide 26: Project Outcomes: Schedule Variance
qc2a. How much shorter was the final schedule from the original schedule?
For projects with a shorter schedule, there were no differences in length between best and typical projects
Chart: How much shorter was schedule
| 1% to 10% | 11% to 25% | 26% to 35% | 36% or more
Best, n=114 | 0.79825 | 0.19298 | 0.0087719 | 0
Typical, n=13 | 0.76923 | 0.076923 | 0.076923 | 0.076923

## Slide 27: Project Outcomes: Schedule Variance
qc2b. How much longer was the final schedule from the original schedule?
For projects with a longer schedule, there were also no differences in length between best and typical projects
Chart: How much longer was final schedule
| 1% to less than 5% | 5% to less than 10%
Best, n=71 | 0.42254 | 0.57746
Typical, n=124 | 0.37097 | 0.62903

## Slide 28: Project Outcomes: Profitability Variance
qc3. How did the profitability of each project compare with your expected profitability at the project onset?
There were significant differences between best and typical projects on profitability, one of the key items for choosing a best project
Typical projects were more likely to be within the expected profit range
Best projects were more likely to have a higher profit than typical projects, with trade contractors most frequently reporting the highest profit levels.
Chart: Profitability variation
| Less than typical for a project of this type | *Within the expected range for a project of this type | *More than typical for a project of this type | Don’t know
Best | 0.03869 | 0.3869 | 0.55357 | 0.020833
Typical | 0.10417 | 0.76786 | 0.10417 | 0.02381

## Slide 29: Project Outcomes: Profitability Variance
qc3a. What was the difference in profit (lower or higher) you experienced?
For projects with a profit variance, best projects were more likely to have a more than 5 percentage point deviation
Chart: Profitability differential
| Less than 2 percentage points | 2 to 5 percentage points | *More than 5 percentage points | Don’t know
Best, n=199 | 0.11558 | 0.40201 | 0.47739 | 0.0050251
Typical, n=70 | 0.31429 | 0.38571 | 0.27143 | 0.028571

## Slide 30: Project Outcomes: Safety Level
qc4. Which of the following best describes the level of safety achieved on each project?
Both typical and best projects achieved good safety outcomes
Typical projects were more likely to have a higher rate of fewer recordable incidents than best projects
Best projects were more likely to achieve the highest level of safety noted, with no recordable incidents or lost time
Chart: Safety level achieved
| More incidents/recordables than average; Notable lost time; Multiple OSHA citations | Average recordable incidents; An OSHA citation; Some lost time | *Fewer recordable incidents than typical; No OSHA citations; No harm to the public; Good safety culture on our team | *No lost time; No recordable incidents or harm to the public; Good safety culture shared by all companies onsite
Best | 0.0029762 | 0.047619 | 0.22024 | 0.72917
Typical | 0.0089286 | 0.10714 | 0.40476 | 0.47917

## Slide 31: Project Outcomes: Safety Level
qc4. Which of the following best describes the level of safety achieved on each project?
For Best projects, significantly more GC/CMs than trade contractors place themselves in the “Good” category, and significantly more trade contractors place themselves in the “Excellent” category than other types of contractors.
There were no significant differences in safety evaluations on typical projects.
Best Projects | GC/CM | Trades | Civil
Fewer recordable incidents than typical; No OSHA citations; No harm to the public; Good safety culture on our team | 28%* | 12%* | 22%
No lost time; No recordable incidents or harm to the public; Good safety culture shared by all companies onsite | 69% | 84%** | 63%
* denote statistical difference with one factor
** denotes statistical difference with more than one factor

## Slide 32: Project Outcomes: Final Quality
qc5. What was the quality of the final building compared with overall expectations?
Both types of projects also achieved good quality outcomes, the other main item for choosing a best project
Typical projects were more likely to meet more or most necessary features
Best projects were more likely to exceed project expectations with no substantial items on the punchlist
Chart: Final quality achieved
| Significantly below initial expectations/failure (i.e., disappointing features significant rework prior to punch list, o | Few/Some expectations met, but not all (i.e., minimum features, remaining punchlist items, remaining warranty call-backs | *More/Most expectations met (I.e., necessary features, punch list completed in 90 days, no ongoing warranty call-backs) | *Exceeded expectations (i.e., exceeded features, no substantial items on the punchlist, no warranty call-backs)
Best | 0.0029762 | 0.0625 | 0.41369 | 0.52083
Typical | 0.0089286 | 0.14583 | 0.6756 | 0.16964

## Slide 33: Project Outcomes: Company Culture
qc6. Where along the spectrum below did each project fall in terms of its impact on the firm culture within your company?
Typical projects were more likely to report that some team members felt empowered
Best projects were significantly better at making all team members feeling full empowered and they had an opportunity for growth or learning
Significantly more trade contractors (19%) than GC/CMs (9%)find that they reinforced traditional roles on typical projects.
Chart: Company culture
| Reinforced traditional roles and did not provide opportunities for growth/learning | *Some team members felt empowered, and there were some opportunities for growth/learning | Most team members felt empowered and felt given a chance for growth/learning | *All team members were fully empowered; all team members had opportunities for growth/learning and to excel on the projec
Best | 0.056548 | 0.14881 | 0.45238 | 0.34226
Typical | 0.125 | 0.34821 | 0.42262 | 0.10417

## Slide 34: Project Outcomes: Team Cohesion
qc7. Which of the following is true about each project, related to how the external team worked together?
On best projects respondents significantly more frequently noted wanting to actively seek opportunities to work with that team again and that the owner was a strategic partner
Significantly more GC/CMs (59%) than trades (36%) report that the owner was a strategic partner during construction on best projects, and GC/CMs (40%) are significantly higher for typical projects in this category than both trades (14%) and civil contractors (27%).
Significanltly more trade contractors (9%) report that none of these apply to their typical projects than do GC/CMs (3%) or civil contractors (0%)
Chart: Team cohesion
| *I would actively seek opportunities to work with that team again | Project team members onsite were supportive of each other | *Owner was a strategic partner during construction | Had repeat work with that owner | None of these
Best | 0.6131 | 0.5119 | 0.50298 | 0.54464 | 0.0059524
Typical | 0.33036 | 0.54464 | 0.3006 | 0.46429 | 0.044643

## Slide 35: Findings
Selection of Best v. Typical projects
Project Outcomes
Organizational Factors
Commercial Factors
Process/Operational Factors
Unless otherwise noted sample size is:
Total: 336 respondents
GC/CM: 187
Specialty: 108
Heavy civil: 41

## Slide 36: Organizational Factors: Team Chemistry
qd1. On a scale of 1 to 4, how would the majority of key stakeholders rate the team chemistry on these specific projects?
Typical projects were more likely to report a fair or good team chemistry
Best projects were more likely to report an excellent team chemistry
GC/CMs report fair team chemistry (14%) significantly less frequently than do trades (28%) or civil contractors (32%)
Chart: Team chemistry
| Poor | *Fair | *Good | *Excellent
Best | 0.0029762 | 0.047619 | 0.36012 | 0.58929
Typical | 0.020833 | 0.20833 | 0.63095 | 0.13988

## Slide 37: Organizational Factors: Timeliness of Communication
qd2. On a scale of 1 to 4, how would the majority of key stakeholders rate the timeliness of communication on these specific projects?
Typical projects were more likely to note that communication was occasionally or frequently on time
Best projects were more likely to note always on time communication
Chart: Timeliness of communications
| Never on time | *Occasionally on time | *Frequently on time | *Always on time
Best | 0 | 0.056548 | 0.49107 | 0.45238
Typical | 0.014881 | 0.24405 | 0.61607 | 0.125

## Slide 38: Organizational Factors: Commitment to Project Goals
qd3. On a scale of 1 to 4, how would the majority of key stakeholders rate how committed all project team members were to the same project goals on these specific projects?
Respondents for typical projects were more likely to state a general commitment to projects
On best projects respondents stated a complete commitment to project goals more frequently
Trades (10%) significantly less frequently report complete commitment to the same project goals on typical projects than do GC/CMs (22%)
Chart: Commitment to project goals
| No commitment shared by project team members on combined project goals/each team member had their own individual company | Minimal commitment to the same project goals | *General commitment to the same project goals | *Complete commitment to the same project goals
Best | 0.0059524 | 0.017857 | 0.37202 | 0.60417
Typical | 0.014881 | 0.095238 | 0.70833 | 0.18155

## Slide 39: Organizational Factors: Integration of Team Members
qd4. On a scale of 1 to 4, how would the majority of key stakeholders describe the integration of project team members on these specific projects?
On typical projects key stakeholders were more frequently viewed as sometimes acting in the interest of optimizing the whole projects
For best projects the stakeholders were more frequently seen to be working cohesively together to optimize the whole and to create workflow to deliver value
Chart: Integration of team members
| Key stakeholders acted primarily/solely for their own benefit on project deliverables | *Key stakeholders sometimes acted in the interest of the project to optimize the whole | Key stakeholders often acted in the interest of the project to optimize the whole | *Key stakeholders worked cohesively together to optimize the whole, to create workflow and to deliver value to the end us
Best | 0.020833 | 0.044643 | 0.43155 | 0.50298
Typical | 0.050595 | 0.3125 | 0.52381 | 0.1131

## Slide 40: Organizational Factors: Integration of Team Members
qd4. On a scale of 1 to 4, how would the majority of key stakeholders describe the integration of project team members on these specific projects?
There are no statistically significant differences for integration of team members on best projects.
However, on typical projects, trades significantly more frequently report that key stakeholders act primarily for their own benefit than do GCs/CMs, and civil contractors significantly more frequently report that key stakeholders sometimes act in the interest of the project to optimize the whole than do GCs/CMs.
Typical Projects | GC/CM | Trades | Civil
Key stakeholders acted primarily/solely for their own benefit on project deliverables | 2%* | 11%* | 2%
Key stakeholders sometimes acted in the interest of the project to optimize the whole | 28%* | 30% | 49%*
* denote statistical difference with one factor
** denotes statistical difference with more than one factor

## Slide 41: Findings
Selection of Best v. Typical projects
Project Outcomes
Organizational Factors
Commercial Factors
Process/Operational Factors
Unless otherwise noted sample size is:
Total: 336 respondents
GC/CM: 187
Specialty: 108
Heavy civil: 41

## Slide 42: Commercial Factors: Initial Engagement of My Company
qe1. Thinking of the best/typical project, when was my company first engaged and contracted on this specific project?
Typical and best projects did not significantly differ as to stage of the project for when a respondent noted their company’s first engagement
Chart: When was my company first engaged
| Pre business case | Business case validation (pre-design) | During conceptualization (0-15% design) | During schematic design (15% 30%) | During design development (30%-60%) | During construction documents (60%-90%) | End of construction documents or later (100% CD)
Best | 0.12798 | 0.14286 | 0.17857 | 0.1131 | 0.125 | 0.1756 | 0.1369
Typical | 0.077381 | 0.080357 | 0.14881 | 0.10119 | 0.10119 | 0.23214 | 0.25893

## Slide 43: Commercial Factors: Initial Engagement of My Company
qe1. Thinking of the best/typical project, when was my company first engaged and contracted on this specific project?
GC/CMs are more frequently selected pre-business case or during business case validation on best projects and during construction documents or later on typical ones.
Chart: GC/CM
| Pre business case | Business case validation (pre-design) | During conceptualization (0-15% design) | During schematic design (15% 30%) | During design development (30%-60%) | During construction documents (60%-90%) | End of construction documents or later (100% CD)
Best | 0.17647 | 0.2139 | 0.20321 | 0.090909 | 0.069519 | 0.12834 | 0.11765
Typical | 0.11765 | 0.1123 | 0.18182 | 0.12299 | 0.069519 | 0.19251 | 0.20321

## Slide 44: Commercial Factors: Initial Engagement of My Company
qe1. Thinking of the best/typical project, when was my company first engaged and contracted on this specific project?
The real gap between best and typical projects opens up for trade contractors in the during construction documents phase or later, when they are more frequently brought on for typical than for best projects.
Chart: Trade Contractors
| Pre business case | Business case validation (pre-design) | During conceptualization (0-15% design) | During schematic design (15% 30%) | During design development (30%-60%) | During construction documents (60%-90%) | End of construction documents or later (100% CD)
Best | 0.064815 | 0.074074 | 0.14815 | 0.14815 | 0.22222 | 0.21296 | 0.12963
Typical | 0.027778 | 0.037037 | 0.12963 | 0.074074 | 0.14815 | 0.30556 | 0.27778

## Slide 45: Commercial Factors: Initial Engagement of My Company
qe1. Thinking of the best/typical project, when was my company first engaged and contracted on this specific project?
The largest difference between best and typical projects for civil contractors is that nearly half (45%) of typical projects involve bringing the contractor in at the end of CDs or later, compared to just about one quarter (24%) of best projects
Chart: Civil Contractors
| Pre business case | Business case validation (pre-design) | During conceptualization (0-15% design) | During schematic design (15% 30%) | During design development (30%-60%) | During construction documents (60%-90%) | End of construction documents or later (100% CD)
Best | 0.073171 | 0 | 0.14634 | 0.12195 | 0.12195 | 0.29268 | 0.2439
Typical | 0.02439 | 0.04878 | 0.04878 | 0.073171 | 0.12195 | 0.21951 | 0.46341

## Slide 46: Commercial Factors: Initial Engagement of Key Trade Contractors
qe2. Thinking of the best/typical project, when were the key trade contractors first engaged and contracted on this specific project?
On typical projects key trade contractors were more frequently reported being first engaged and the end of construction documents or later
A much larger share of civil contractors report that key trade contractors were first engaged at the end of CDs for both best (44%) and typical (56%) projects than do GC/CMs (17% and 35%, respectively).
Chart: When were key trade contactors first engaged
| Pre business case | Business case validation (pre-design) | During conceptualization (0-15% design) | During schematic design (15% 30%) | During design development (30%-60%) | During construction documents (60%-90%) | *End of construction documents or later (100% CD)
Best | 0.014151 | 0.066038 | 0.16038 | 0.16509 | 0.17925 | 0.21226 | 0.20283
Typical | 0.009434 | 0.051887 | 0.080189 | 0.10849 | 0.16509 | 0.20755 | 0.37736

## Slide 47: Commercial Factors: Project Delivery Method
qe3/5. Thinking of the best project, what was the delivery method for this specific project?
There were no significant differences in project delivery method between best and typical projects
Design-bid-build was most frequent followed by CM at risk and IPD was least frequently used
GC/CMs are involved in CM-at-Risk projects more frequently for both best (34%) and typical (39%) projects than are trades (16%/20%) and civil contractors (5%/0%).
For typical projects only, a significantly higher percentage of civil contractors (63%) are involved in design-bid-build projects, and more trade contractors (22%) are involved in design-build based on initial design/bridging documents
Chart: Project delivery method
| Design-bid-build | Construction Management at Risk | Design-build based on initial design/bridging documents | Design-build/EPC/Turnkey based on program/requirements | Integrated project delivery (multi-party agreement) | Other
Best | 0.3006 | 0.24702 | 0.21726 | 0.10119 | 0.083333 | 0.050595
Typical | 0.38095 | 0.28274 | 0.14286 | 0.065476 | 0.074405 | 0.053571

## Slide 48: Commercial Factors: Design-Build Approach
qe4/6. Which of the following best describes the approach to design/build on your best project?
On projects that design-build was used the approach did not differ between best and typical projects
Contractor-led was most frequently used
Chart: Design-build approach
| Architect/Engineer-led | Contractor-led | Other
Best, n=107 | 0.28037 | 0.68224 | 0.037383
Typical, n=70 | 0.32857 | 0.64286 | 0.028571

## Slide 49: Commercial Factors: Design-Assist Use
qe7. Was Design-Assist part of your typical and/or best project?
Design-assist was used significantly more frequently on best projects
Chart: Design-assist used?
| *Yes | *No
Best, n=82 | 0.63415 | 0.36585
Typical, n=82 | 0.30488 | 0.69512

## Slide 50: Commercial Factors: Procurement Process
qe8/9. Thinking of the best/typical project, what process was used for procurement?
Typical projects were more likely to use an open bid process
While there were no significant differences in procurement processes for best projects between the different types of contractors, for typical projects, open bid was used significantly less frequently on GC/CM projects (34%) than for trades (52%) and civil contractors (61%), and prequalified bids were used significantly more frequently for GC/CM projects (35%) than for trades (21%),
Chart: Procurement process
| *Open Bid | Prequalified Bid | RFP | Sole-Source | Other, please specify:
Best | 0.22619 | 0.40774 | 0.23214 | 0.1131 | 0.020833
Typical | 0.43155 | 0.28869 | 0.20536 | 0.056548 | 0.017857

## Slide 51: Commercial Factors: Selection Criteria
qe10/11. Thinking of the best/typical project, what selection criteria was used for procurement?
There were no significant differences for types of procurement processes used between best and typical projects
Bid price is more common among civil contractors than GC/CMs and Fee & GCs more commonly by GC/CMs than by trade or civil contractors for both best and typical projects. However, the basic pattern below still holds for each.
Chart: Selection criteria
| Bid price | Fee & GCs (no bid) | Technical qualifications | Design requirements | Technical proposal | Similar project experience | Interview | Other
Best | 0.63095 | 0.18452 | 0.4256 | 0.056548 | 0.27976 | 0.52976 | 0.30952 | 0.02381
Typical | 0.79167 | 0.17262 | 0.31845 | 0.053571 | 0.19345 | 0.36607 | 0.18155 | 0.02381

## Slide 52: Findings
Selection of Best v. Typical projects
Project Outcomes
Organizational Factors
Commercial Factors
Process/Operational Factors
Unless otherwise noted sample size is:
Total: 336 respondents
GC/CM: 187
Specialty: 108
Heavy civil: 41

## Slide 53: Process Factors: Intentional Project Formation
qf1. Which of the following Intentional Project Formation/Team Development Practices (not used as a recovery method) occurred during the pre-construction or construction phase on your best and typical projects?
Best projects were more likely to establish conditions of satisfaction key stakeholders needed to achieve as a team to feel satisfied
Chart: Intentional project formation/team development practices
| Handoff practices to convey preconstruction/estimating knowledge to construction team | The owner provided a statement that captured their abstract goals construction phase | *Conditions of Satisfaction were created that explicitly described what key stakeholders (Owner/ A&E/ Builders) including my company needed to achieve as a team to feel satisfied | Conducted a disciplined and continuous onboarding process for all new team members co | Utilized co-location and multifunctional work groups to advance the work/solve problems/make decisions together | Regular (e.g., quarterly) team health assessments/ checks construction phase on your | None of these construction phase on your best and typical projects?
Best | 0.50595 | 0.22024 | 0.39286 | 0.30655 | 0.27381 | 0.25595 | 0.14583
Typical | 0.41071 | 0.11607 | 0.24702 | 0.22024 | 0.15774 | 0.1875 | 0.22619

## Slide 54: Process Factors: Intentional Project Formation
qf1. Which of the following Intentional Project Formation/Team Development Practices (not used as a recovery method) occurred during the pre-construction or construction phase on your best and typical projects?
GC/CMs more frequently do regular team health assessments than trade contractors, but all three types more frequently do them on their best projects than their typical ones.
GC/CMs are the most frequent users of at least one of these activities.
Regular (e.g., quarterly) team health assessments/ checks | GC/CM | Trades | Civil
Best | 33%* | 16%* | 20%
Typical | 27%* | 7%* | 12%
None of these | GC/CM | Trades | Civil
Best | 11% | 17% | 24%
Typical | 15%* | 31% | 37%
* denote statistical difference with one factor
** denotes statistical difference with more than one factor

## Slide 55: Process Factors: Design/Preconstruction Practices
qf2. Which of the following Design/Preconstruction Practices occurred during the pre-construction phase on your best and typical projects?
Best projects significantly conducted more design practices including; budget estimates at major phases of design, tested concept design against project goals, an iterative design process informed by continuous review and validated against outcomes, and developed a production plan identifying main project phases
Chart: Design/preconstruction practices
| *Budget estimates and/or value engineering conducted at major phases of design | *Diverse group, including my company, tested concept design against project goals and constraints (e.g., schedule and budget) to sign off on recommendation | Development of a cost-model, which is segregated into major systems or building elements to steer design with the project stakeholders | *Design developed with project stakeholders using sets of alternative solutions and informed by continuous review and validation of cost, schedule and design, tightly coupled with customer value | Construction was released in small packages based on design intent and team risk analysis | *Developed a production plan for the project identifying main project phases, plan for prefabrication/ modularization, overall supply chain needs, long lead items | None of these
Best | 0.59524 | 0.29464 | 0.30655 | 0.3631 | 0.22024 | 0.39286 | 0.13988
Typical | 0.44643 | 0.14583 | 0.19345 | 0.20536 | 0.16071 | 0.2381 | 0.25

## Slide 56: Process Factors: Design/Preconstruction Practices
qf2. Which of the following Design/Preconstruction Practices occurred during the pre-construction phase on your best and typical projects?
There are many differences by type of contractor in the frequency of use of design/preconstruction practices for both best and typical projects
Budget estimates and/or value engineering conducted at major phases of design | GC/CM | Trades | Civil
Best | 65% | 54% | 49%
Typical | 52%** | 38% | 27%
Diverse group, including my company, tested concept design against project goals and constraints (e.g., schedule and budget) to sign off on recommendation | GC/CM | Trades | Civil
Best | 36%* | 23% | 15%*
Typical | 20% | 9% | 5%
Development of a cost-model, which is segregated into major systems or building elements to steer design with the project stakeholders | GC/CM | Trades | Civil
Best | 40%** | 20% | 15%
Typical | 25%* | 15% | 5%*
Design developed with project stakeholders using sets of alternative solutions and informed by continuous review and validation of cost, schedule and design, tightly coupled with customer value | GC/CM | Trades | Civil
Best | 46%** | 25% | 24%
Typical | 27%* | 11%* | 15%
* denote statistical difference with one factor
** denotes statistical difference with more than one factor

## Slide 57: Process Factors: Design/Preconstruction Practices
qf2. Which of the following Design/Preconstruction Practices occurred during the pre-construction phase on your best and typical projects?
There are many differences by type of contractor in the frequency of use of design/preconstruction practices for both best and typical projects
GC/CMs are most frequently using at least one of these practices, especially on typical projects.
* denote statistical difference with one factor
** denotes statistical difference with more than one factor
Construction was released in small packages based on design intent and team risk analysis | GC/CM | Trades | Civil
Best | 29%* | 13%* | 15%
Typical | 20% | 13% | 7%
None of these | GC/CM | Trades | Civil
Best | 10%* | 16% | 27%*
Typical | 18%** | 30% | 44%

## Slide 58: Process Factors: Communication and Information Exchange
qf3. Which of the following best describes how the team communicated and how information was exchanged during the construction phase on your best and typical projects?
Best projects held regular team meetings focused on reporting out issue identification more frequently than typical projects
Chart: Communication and information exchange
| *Held regular team meetings focused on reporting out issue identification | Short daily stand-up team sessions to verify plan status and needs with rotating leadership | A disciplined approach to make the steps in a process visual so status of system/key performance indicators can be understood at a glance | Electronic information exchange (paperless project) | Planning for implementation of BIM using a structured process to define uses, information hand-offs , and deliverables | BIM 3D coordination/clash detection | BIM 4D and site logistic planning | None of these
Best | 0.72619 | 0.31845 | 0.28274 | 0.58333 | 0.30952 | 0.28869 | 0.071429 | 0.035714
Typical | 0.59524 | 0.26488 | 0.16964 | 0.5119 | 0.17857 | 0.1875 | 0.026786 | 0.074405

## Slide 59: Process Factors: Communication and Information Exchange
qf3. Which of the following best describes how the team communicated and how information was exchanged during the construction phase on your best and typical projects?
Many significant differences exist for best and typical by contractor type for communication and information exchange, they are noted in the following tables
* denote statistical difference with one factor
** denotes statistical difference with more than one factor
Held regular Owner-Architect/Engineer-Contractor meetings focused on reporting out issue identification | GC/CM | Trades | Civil
Best | 79% | 61%* | 73%
Typical | 74% | 34%* | 58%
Planning for implementation of building information modeling (BIM) using a structured process to define uses, information hand-offs , and deliverables | GC/CM | Trades | Civil
Best | 37% | 28% | 10%*
Typical | 23% | 15% | 2%*
BIM 3D coordination/clash detection | GC/CM | Trades | Civil
Best | 12% | 2%* | 0%
Typical | 5% | 8% | 17%*
A disciplined approach to make the steps in a process visual so status of system/key performance indicators can be understood at a glance | GC/CM | Trades | Civil
Best | 32% | 22% | 26%
Typical | 23% | 8%* | 10%

## Slide 60: Process Factors: Communication and Information Exchange
qf3. Which of the following best describes how the team communicated and how information was exchanged during the construction phase on your best and typical projects?
More differences for communication and information exchange
* denotes statistical difference with one factor
** denotes statistical difference with more than one factor
Electronic information exchange (paperless project) | GC/CM | Trades | Civil
Best | 52% | 56% | 49%
Typical | 57% | 49% | 31%*
None of these | GC/CM | Trades | Civil
Best | 3% | 3% | 7%
Typical | 5% | 8% | 17%*

## Slide 61: Process Factors: Safety Practices
qf4. Which of the following Safety Practices occurred during the construction phase on your best and typical projects?
Best projects were more likely to use a disciplined approach to maintain orderly site than were typical projects
Chart: Safety practices
| Safety professionals involved in every aspect of preconstruction planning | Weekly safety inspections led by GC and participated in by contractor stakeholders | Daily job hazard analysis/pre-task planning | Reporting of positive and compliance observations by trade workers and/or safety professionals | *A disciplined approach to maintain orderly site (exceptional housekeeping, nothing hits the floor, 5S) | Root cause analysis on recordable or high potential incidents | None of these
Best | 0.36607 | 0.6756 | 0.63988 | 0.47321 | 0.5119 | 0.34226 | 0.056548
Typical | 0.2619 | 0.58631 | 0.58929 | 0.37202 | 0.34821 | 0.27679 | 0.080357

## Slide 62: Process Factors: Safety Practices
qf4. Which of the following Safety Practices occurred during the construction phase on your best and typical projects?
For safety practice there were many significant differences among contractor types noted in the tables below
* denotes statistical difference with one factor
** denotes statistical difference with more than one factor
Reporting of positive and compliance observations by trade workers and/or safety professionals | GC/CM | Trades | Civil
Best | 54% | 37%* | 47%
Typical | 44% | 27%* | 34%
Root cause analysis on recordable or high potential incidents | GC/CM | Trades | Civil
Best | 40% | 24%* | 37%
Typical | 33% | 18%* | 29%
Safety professionals involved in every aspect of preconstruction planning | GC/CM | Trades | Civil
Best | 40% | 28% | 44%
Typical | 31% | 16%* | 32%
Weekly safety inspections led by GC and participated in by contractor stakeholders | GC/CM | Trades | Civil
Best | 72% | 66% | 54%
Typical | 69% | 44%* | 49%
A disciplined approach to maintain orderly site (exceptional housekeeping, nothing hits the floor, 5S) | GC/CM | Trades | Civil
Best | 54% | 46% | 49%
Typical | 42% | 27%* | 24%

## Slide 63: Process Factors: Planning and Scheduling Practices
qf5. Which of the following Planning and Scheduling Practices occurred during the construction phase on your best and typical projects?
Best projects were more likely to have key stakeholders to help define project milestones and develop plans for phases working backwards to determine handoffs, and define weekly task lists and measure the percentage of tasks completed to make necessary adjustments to plans
Chart: Planning and scheduling practices
| CPM/baseline schedules are regularly published for review at OAC meetings | *Key stakeholders define project milestones and develop plans for specific phases working backwards to determine handoffs | *Key stakeholders proactively review upcoming tasks to confirm their plan, identify and remove obstacles/road blocks | Key stakeholders define a list of tasks to be completed within a week and regularly measure the percentage of tasks completed vs planned and make adjustments as necessary | Production scheduling focused on detailed planning of worker and crew level tasks at short intervals (15 or 20 minute) for highly repetitive work to smooth workflow | Implementation of multi-trade prefabrication /modularization | None of these
Best | 0.62202 | 0.55655 | 0.58333 | 0.46131 | 0.2381 | 0.21131 | 0.050595
Typical | 0.54464 | 0.41369 | 0.39583 | 0.30357 | 0.15774 | 0.095238 | 0.10714

## Slide 64: Process Factors: Planning and Scheduling Practices
qf5. Which of the following Planning and Scheduling Practices occurred during the construction phase on your best and typical projects?
For planning and scheduling practices only two differences were noted among contractor groups for items; CPM/baseline schedules are regularly published, and Key stakeholders define a list of tasks to be completed within a week and regularly measure the percentage of tasks completed vs planned and adjust as necessary
* denotes statistical difference with one factor
** denotes statistical difference with more than one factor
CPM/baseline schedules are regularly published for review at OAC meetings | GC/CM | Trades | Civil
Best | 76% | 46%* | 54%
Typical | 68% | 37%* | 39%
Key stakeholders define a list of tasks to be completed within a week and regularly measure the percentage of tasks completed vs planned and make adjustments as necessary | GC/CM | Trades | Civil
Best | 52% | 44% | 27%*
Typical | 37% | 25% | 12%*

## Slide 65: Process Factors: Quality Practices
qf6. Which of the following Quality Practices occurred during the construction phase on your best and typical projects?
Use of contract required mock-ups, in-process quality checklists and tracking of quality issues during construction and engaging workers directly in identifying and solving problems were practices more frequently conducted on best projects
Chart: Quality practices
| *Use of contract required mock-ups, in-process quality checklists and tracking of quality issues during construction | Design informed by material cut sheets from contracted trade partners/vendors | Team initiated mock-ups/first run studies/early prototyping of distinct features/typical components | Walking the job site to identify waste elimination opportunities | Identification of a portion of the workplace to be observed and look for inefficiencies | *Engage workers directly in identifying and solving problems | None of these
Best | 0.52976 | 0.52083 | 0.29464 | 0.43452 | 0.26488 | 0.58631 | 0.059524
Typical | 0.36905 | 0.43155 | 0.19345 | 0.33929 | 0.18452 | 0.43155 | 0.11012

## Slide 66: Process Factors: Quality Practices
qf6. Which of the following Quality Practices occurred during the construction phase on your best and typical projects?
Many significant differences exist among contractor types for quality practices, see tables for specific differences
* denotes statistical difference with one factor
** denotes statistical difference with more than one factor
Use of contract required mock-ups, in-process quality checklists and tracking of quality issues during construction | GC/CM | Trades | Civil
Best | 65%** | 45% | 32%
Typical | 48%** | 23% | 22%
Team initiated mock-ups/first run studies/early prototyping of distinct features/typical components | GC/CM | Trades | Civil
Best | 37%** | 22% | 15%
Typical | 24% | 15% | 12%
Walking the job site to identify waste elimination opportunities | GC/CM | Trades | Civil
Best | 48% | 40% | 32%
Typical | 41% | 23%* | 29%
Identification of a portion of the workplace to be observed and look for inefficiencies | GC/CM | Trades | Civil
Best | 32% | 19% | 22%
Typical | 24% | 12%* | 12%
None of these | GC/CM | Trades | Civil
Best | 4% | 7% | 10%
Typical | 6%** | 17% | 20%

## Slide 67: Process Factors: Budget Management & Cost Control Practices
qf7. Which of the following Budget Management/Cost Control Practices occurred during the construction phase on your best and typical projects?
Budget management/cost control practices were consistent across best and typical projects, no significant differences in any practices were found
Chart: Budget management/cost control practices
| Thorough vetting and scope review of subcontractors prior to award and monthly forecasting of costs | Award of key scopes of work reviewed with customer and any savings/ overrun from original budget is the responsibility of the customer | Project contingency jointly managed with the customer and savings shared at project completion | Detailed weekly production analysis and forecasting of costs for critical activities | Team incentivized to manage to budget with open book accounting of all costs and continuous review of risks and opportunities during the course of construction to adjust/make decisions | None of these
Best | 0.60417 | 0.3125 | 0.37202 | 0.42262 | 0.29762 | 0.1369
Typical | 0.51488 | 0.21726 | 0.25298 | 0.3244 | 0.20238 | 0.21131

## Slide 68: Process Factors: Budget Management & Cost Control Practices
qf7. Which of the following Budget Management/Cost Control Practices occurred during the construction phase on your best and typical projects?
Budget management/cost control practices were consistent across best and typical projects, however significant differences among contractor groups were found and are noted below
* denotes statistical difference with one factor
** denotes statistical difference with more than one factor
Thorough vetting and scope review of subcontractors prior to award and monthly forecasting of costs | GC/CM | Trades | Civil
Best | 73%** | 46% | 42%
Typical | 67%** | 31% | 34%
Project contingency jointly managed with the customer and savings shared at project completion | GC/CM | Trades | Civil
Best | 53%** | 15% | 24%
Typical | 35% | 10%* | 22%
Team incentivized to manage to budget with open book accounting of all costs and continuous review of risks and opportunities during the course of construction to adjust/make decisions | GC/CM | Trades | Civil
Best | 36% | 18%* | 29%
Typical | 26% | 8%** | 24%
Detailed weekly production analysis and forecasting of costs for critical activities | GC/CM | Trades | Civil
Best | 45% | 37% | 44%
Typical | 37% | 22%* | 29%
None of these | GC/CM | Trades | Civil
Best | 6%** | 26% | 17%
Typical | 8%** | 42% | 27%

## Slide 69: Process Factors: Building Turnover and Activation Practices
qf8. Which of the following building turnover/activation practices occurred following the construction phase on your best and typical projects?
Best projects were more likely to use a collaborative, transparent turn-over in small batches practice than typical projects
Chart: Building turnover/activation practices
| Standard check for performance of contractual duties outlined in the contract related to commissioning, as-builts, punch list and substantial completion | *Collaborative, transparent turn-over in small batches; substantial completion a formality | Electronic final documentation turnover (e.g., OMSI, Cobie) | Post-occupancy evaluations at regular intervals (e.g., 6 months, 11 months) focused on technical work/material performance | Ongoing post-occupancy performance retrospective focused on operational and experiential performance | None of these
Best | 0.68155 | 0.36607 | 0.47619 | 0.3125 | 0.19048 | 0.077381
Typical | 0.65179 | 0.20238 | 0.41369 | 0.1994 | 0.095238 | 0.095238

## Slide 70: Process Factors: Building Turnover and Activation Practices
qf8. Which of the following building turnover/activation practices occurred following the construction phase on your best and typical projects?
Building turnover and activation practices had several significant differences among contractor groups, noted in tables below
* denotes statistical difference with one factor
** denotes statistical difference with more than one factor
Standard check for performance of contractual duties outlined in the contract | GC/CM | Trades | Civil
Best | 44% | 29%* | 24%
Typical | 27% | 13%* | 10%
Electronic final documentation turnover | GC/CM | Trades | Civil
Best | 59%** | 36% | 27%
Typical | 50%** | 32% | 24%
Post-occupancy evaluations at regular intervals focused on technical work/material performance | GC/CM | Trades | Civil
Best | 41%** | 21% | 12%
Typical | 30%** | 7% | 5%
Ongoing post-occupancy performance retrospective focused on operational and experiential performance | GC/CM | Trades | Civil
Best | 26%** | 13% | 5%
Typical | 13% | 5% | 5%
Standard check for performance of contractual duties outlined in the contract | GC/CM | Trades | Civil
Best | 69% | 69% | 61%
Typical | 72% | 56%* | 61%
None of these | GC/CM | Trades | Civil
Best | 3%** | 12% | 20%
Typical | 3%** | 16% | 22%

## Slide 71: Process Factors: Issue Resolution & Decision-Making Practices
qf9. Which of the following were issue resolution/problem solving/decision-making practices used on your best and typical projects?
Using a formal decision-making system for determining the best decision by looking at the advantages of each option was more frequently done on best projects than typical ones
Chart: Issue resolution/problem solving/decision-making practices
| Problem solving/decision making occurred based solely on leader’s opinion or on lowest initial cost | Used a disciplined approach/retrospective to regularly discuss after an event what was successful and could be improved | Used a systematic, formal approach for analyzing possible causes to determine the root cause of a problem | *Used a formal decision-making system for determining the best decision by looking at the advantages of each option | Employed a formal collaborative problem-solving process that defines the problem, creates alignment among stakeholders, identifies the current state, defines goals, analyzes gaps and recommends solutions | Employed an ongoing and formal method of continuous improvement by making incremental changes initiated by anyone when an abnormality was detected | None of these
Best | 0.3006 | 0.38393 | 0.35417 | 0.40476 | 0.24702 | 0.1994 | 0.089286
Typical | 0.41369 | 0.25893 | 0.23512 | 0.25893 | 0.13393 | 0.12798 | 0.1369

## Slide 72: Process Factors: Issue Resolution & Decision-Making Practices
qf9. Which of the following were issue resolution/problem solving/decision-making practices used on your best and typical projects?
Significant difference among contractor groups for issue resolution and decision-making practices are noted below
Used a disciplined approach to discuss after an event what was successful and could be improved | GC/CM | Trades | Civil
Best | 45% | 28%* | 36%
Typical | 31% | 19% | 24%
Used a formal approach to determine the root cause of a problem | GC/CM | Trades | Civil
Best | 40% | 26%* | 39%
Typical | 29% | 14%* | 24%
* denotes statistical difference with one factor
** denotes statistical difference with more than one factor
Employed a collaborative process defining the problem, create alignment among stakeholders, identify the current state, defines goals, analyzes gaps and recommends solutions | GC/CM | Trades | Civil
Best | 32% | 15%* | 17%
Typical | 18% | 6%* | 15%
Used a decision-making system for determining the best decision by looking at the advantages of each option | GC/CM | Trades | Civil
Best | 46% | 37% | 27%
Typical | 33% | 16%* | 22%
Standard check for performance of contractual duties outlined in the contract | GC/CM | Trades | Civil
Best | 69% | 69% | 61%
Typical | 72% | 56%* | 61%
None of these | GC/CM | Trades | Civil
Best | 5% | 15%* | 10%
Typical | 10% | 18% | 20%